## Task List
Week # | Task # | Task Description | Estimated Time (Hours) | Member Responsible
8 | 1 | Create draft mock-up design for web app. | 6 | James
8 | 2 | Decide on characteristics that the app aims to teach empathy on. | 2 | James | Total Hours | 202
8 | 3 | Create initial set of starter questions to allow the users to get to know each other without talking about the controversial topic. | 3 | Vincent
8 | 4 | Decide on NLP features to include in web app. | 5 | Vincent | James | 101
9 | 5 | Research characteristics and come up with literature library with articles with both points of view. | 5 | James | Vincent | 101
9 | 6 | Create discussion questions for each topic. | 6 | Vincent
9 | 7 | Finalize design for web-app. | 4 | Vincent
10 | 8 | Propose conversation structure for each topic. | 7 | James
10 | 9 | Write survey questions for users to evaluate their experience as they use the app. | 3 | Vincent
10 | 10 | Finalize schema document for the web app (James). | 12 | James
10 | 11 | Finalize schema document for the web app (Vincent). | 12 | Vincent
INTERMEDIATE MILESTONE 1 DUE
11 | 12 | Design database structure for web app. | 6 | Vincent
11 | 13 | Build barebones Django App. | 10 | James
11 | 14 | Choose/write match-making algorithm. | 3 | Vincent
12 | 15 | Write SQL queries for the web app. | 6 | James
12 | 16 | Incorporate basic functionality into the web app. | 11 | Vincent
12 | 17 | Work on coding logic for half of the structured conversations. | 4 | James
12 | 18 | Work on coding logic for the other half of the structured conversations. | 4 | Vincent
13 | 19 | Start initial work with NLP in preparation for next phase. | 6 | James
13 | 20 | Finalize and test web app with no NLP (James). | 13 | James
13 | 21 | Finalize and test web app with no NLP (Vincent). | 13 | Vincent
INTERMEDIATE MILESTONE 2 DUE
14 | 22 | Recruit 5 or more pilot participants (James). | 3 | James
14 | 23 | Recruit 5 or more pilot participants (Vincent). | 3 | Vincent
14 | 24 | Finish coding NLP functionality in app. | 8 | Vincent
14 | 25 | Test the app extensively. | 5 | James
15 | 26 | Start 1-week pilot with participants. Monitor pilot conversations and intervene as needed. | 10 | James
15 | 27 | Start writing final paper. | 8 | Vincent
15 | 28 | Finalize survey questions to ask pilot partipcants. | 2 | Vincent
16 | 29 | Ask survey respondents to complete brief survey. | 2 | James
16 | 30 | Finish writing final paper (James). | 10 | James
16 | 31 | Finish writing final paper (Vincent). | 10 | Vincent
FINAL PROJECT DUE